## Instructions
Satish Thatte © VersionOne: Agile Template Set, 18-June-2013
1 | Please read this Instructions worksheet first, and then review other worksheet before you start using this template.
This template works best when the ScrumMaster(s) and concerned managers have read my blog on how to Make Release Retrospectives Strategic and Effective, available at the VersionOne blog site.
2 | "Release Retro Example" worksheet provides several examples in a template.
As they are examples, your specific details on strategic objectives, metric, measurement approach, etc., for your enterprise or project are likely to be different.
3 | When you are at an early statge of your agile transition, use only 1 to 3 strategic objectives to stay focused. Over a period 2 to 3 years, you may grow the set of strategic objectives up to 5.

## Release Retro Example
Release Retrospective Template
Product Name, Release Number, Date
ID | Strategic Objectives | Strategic Metric | Measurement Approaches | Identify Issues and Perform Root Cause Analysis | Develop Action Plan | Implement Action Plan
A | Understand and satisfy the real requirements of customers | Field data on product feature usage by customers | Customer surveys to understand which features of a product are being used and how frequently; and which features may be missing or are difficult to use and need to be improved. • Feature usage distribution and frequency (always used, often used, sometime used, rarely used, never used) • Features that are missing • Features that need to be improved • Features that need to be simplified or streamlined | • Identify rarely used or least used features • Identify important missing features • Identify features that give poor user experience or are difficult to use | • Discontinue rarely used or least used features; and guard against adding similar features in future release cycles • Add important missing features in the product backlog • Improve, simplify or streamline features that give poor user experience | It is recommeded that the actions in the action plan be modeled as epics and stories. Epics should be broken down into stories and assigned to sprints in a future release cycle. All these stories should be defined, estimated, planned, implemented, tracked and closed similar to software development stories. This is a very practical and effective way that well-intentioned retrospective epics and stories actually are implemented and the teams and enterprise get the true benefits of retrospectives (inspect, adapt, learn and improve the process).
B | Improve time to market | Concept to Customer value realization cycle time | Measure the cycle time from the concept creation until a feature(s) realizing that concept produces business value for the customer. Various elements of this value chain are broken down as a sequence or a network of steps, and each step is measured in terms of elapsed time. • End-to-end cycle time • End-to-end process bottlenecks • (Value producing time / Total cycle time) ratio for the value chain | • Identify bottlenecks and causes of delays, and waiting periods and buffers in the existing end-to-end process from concept to customer value realization | • Remove identified bottlenecks in the end-to-end process by process reengineering • Reduce end-to-end cycle time by simplifying and streamlining the process, and reduce delays and bottlenecks
C | Reduce release cost (covering development and delivery) | Release cost data in financial terms covering the entire development and delivery cycle | Measure fully loaded development and delivery cost: people, material, equipment, licenses, shared IT service charges, etc. | • Break down the release cost for development and delivery into its component to identify the contribution of different cost components o Cost and opportunity cost represented by rarely used features o Cost represented by poor release productivity o Cost represented by poor level of automation along the end-to-end value chain (automated unit tests, automated QA tests, automated regression test, automated acceptance test, automated build process, lack of continuous integration, etc.) o Cost represented by personnel o Cost represented by equipment (dev and QA environment, build machines o Cost represented by software licenses: Development tools, QA tools | • Reduce development and delivery costs by o eliminating rarely used features (see action plan for measure A above) o improving release productivity (see action plan for measure D below) o increasing automation along the end-to-end value chain o using lower-cost external vendors
D | Improve release productivity for software development and delivery process | Release productivity = Release velocity / Release cost | As a release consists of a sequence of sprints and multiple teams may be involved, it is important to normalize the velocity numbers across sprints and across teams to account for the fact that story points across sprints and teams may represent different amount of work. Without story point normalization, story point math may not make sense. Story point normalization is a complex topic and is outside the scope of this template and the associated blog. | Factors that may have reduced release productivity. Some examples: • Poor performance of cross-functional teams • Low degree of automation • Lack of skills and training issues • Personnel issues • Multiplexing and multitasking | • Improve release velocity by emphasizing better team work, cross-functional team training, automation • Reduce release cost (see action plan for measure C above)
E | Improve quality of products shipped | Number of customer-reported new issues in a given period of time | This metric and its measurement are self-explanatory. Typically this number can be reported on a quarterly basis, or for the entire release cycle. | • Identify issues that could have been prevented with rigorous design review • Identify issues that could have been prevented with rigorous code review • Identify issues that could have been prevented with rigorous unit testing by developers • Identify issues that could have been prevented with rigorous QA testing by QA testers • Identify issues that could have been prevented from more effective customer training and support | • Improve quality with review sessions for feature specification, design, code • Offer training and resources for test-driven development, refactoring, test automation, and technical debt reduction
F | Improve Productivity and Quality concurrently (they should not be traded-off against each other) | Productivity-Quality composite measure = Release Productivity / Number of customer-reported new issues | This measure combines the data from measures D and E. | • Does the metric suggest that the team is treating productivity and quality as two competing factors that must be traded off; any attempt to increase productivity invariably reduces quality, and vice versa? • Identify lack of skills or training issues | • If there is an observed trade-off between Release productivity and Number of customer-reported issues, offer training to break the trade-off mindset. With Quality first, productivity should increase and not go down (don’t fall for a false trade-off tap).